## Sheet3
| Risk Category >>>> | Financial |  | Technical |  | Design |  | Execution |  | Achievement of Carbon Goal
Sub-application | Sub-section | Rate* | Rationale | Rate | Rationale | Rate* | Rationale | Rate* | Rationale | Rate* | Rationale
Waste Heat Recovery | Glycol System | L |  | L | Technical risk mitigated with previous projects | L-M | Project is based on existing industry standard designs but brings improvements which require unique engineering. | L-M | Technically experienced internal and external professionals available for all aspects (piping, electrical, mech). | L | Application design for process and for heat. Confidence of carbon KPI achievement based on similar projects previously achieved.
HE Motors, Compressors, Lighting | Variable Speed Air Compressor System | L |  | L | Technology is known | L | Design criteria for air demand profile, flow, pressure, size, losses, turndown capacity understood and to be adjusted for elevation. Operation designed for BEP. | L | Procurement risk to bring certainty to scope and ability of equipment to meet design criteria. Installation risk limited to tie-in effort and associated piping network. | L | 20% reduction, well accepted and modeled standard
| Lighting | L |  | L | Technology is known, breadth of scope and fixture quantity brings the technical challenge | L | Design criteria illuminance levels, visual comfort, uniformity, type, occupancy sensor location and settings, rated life all understood and planning based on installation learnings from previous projects. | L | Construction as part of larger building and electrical installation. Overall GC and project management structures in place to manage the overall project. | L | LED Fixtures specifically selected for application to ensure achievement of KPI target for GHG.
Industrial Process Equipment Electrification | Vacuum blower program | L |  | M | Vacuum blower themself are known and proven equipment. This new application provide energy and water reduction, with potential for future standardization in manufacturing. | L-M | Equivalent vacuum performance with lower energy requirement. Operated at variable speed reducing motor loads when vacuum demand decreases. | L-M | Project to be executed using standard and best practice construction methods using OEM support. | L | Electricity consumption for the Business as Usual scenario is using actual data from a similar facility, while forecasted electricity consumption for Vacuum blower is calculated with known engineered performances curves of such blower.
| Variable Speed Pumps and Equipment | L |  | L | VFD installation on process equipment - equipment portion known, application provides marginal risk due to overall system integration. | L | In most applications the VFD control scheme will replace a throttle valve. In an operating scenario where demand is lower, the VFD controlled equipment can decrease RPM, increasing efficiency, to meet process requirements. | L | Risk low per installation. Risk increases marginally due to overall integration into larger scope of full site build out. | L | 20% reduction, well accepted and modeled standard
L = Low Risk
M = Medium Risk
H = High Risk